## Slide 1: COCOMO Model
Project Management

## Slide 2: Innovative Visionary Project
Underestimated Effort and Time
Inadequate Resource Allocation
Severe Budget Overruns
Compromised Quality
An ambitious project aimed to revolutionize supply chain management

## Slide 3: COCOMO MODEL
COCOMO stands for "Constructive Cost Model" and was developed by Barry Boehm in 1981.
Designed to calculate the cost of software development using empirical data and formulas.
Accurate estimation of cost, effort, and schedule is crucial for successful software project management.
01

## Slide 4: Modes of COCOMO 01 02 03
Organic
Small teams with good experience working on straightforward projects.
Semi-Detached
Projects of intermediate size and complexity.
Embedded
Complex projects with stringent requirements and hardware constraints
02

## Slide 6: Stages Of COCOMO
Basic
Intermediate
Detailed
03

## Slide 7: Basic COCOMO
Provides an approximate estimate of project parameters.
Based on Lines of Code (LOC)
Estimates:
  Effort: E = Person Months
  Development Time: D =
  People Required: P =

## Slide 8: Basic COCOMO
Where a, b, c & d are COCOMO constants for each mode
Mode | a | b | c | d
Organic | 2.4 | 1.05 | 2.5 | 0.38
Semi-Detached | 3.0 | 1.12 | 2.5 | 0.35
Embedded | 3.6 | 1.20 | 2.5 | 0.32

## Slide 9: Example: Basic COCOMO
Project: Medium Complexity CRM System with 50 KLOC
Calculation:
  Effort = Person Months
  E = 239.86 Person Months
  Development Time =
  D = 17.01 Months
  People Required =

## Slide 10: Intermediate COCOMO
Intermediate COCOMO model refines the initial estimates obtained
Uses an additional set of 15 cost drivers based on various Software Engineering Attributes, called Effort Adjustment Factors (EAF):
  Product Attributes
  Hardware Attributes
  Personnel Attributes
  Project Attributes

## Slide 11: Two Concepts
KLOC Calculation
Initial Cost Estimation based on KLOC as in Basic COCOMO
Effort Adjustment Factors
Effort Adjustment Factors multiplied in order to more accurately estimate

## Slide 12
Effort Adjustment Factors are cost drivers that adjust project effort, categorized into Product, Hardware, Personnel, and Project Attributes, to enhance estimation accuracy.

## Slide 13: Intermediate COCOMO
Calculation Adjustment for Intermediate COCOMO:
Rest of the Calculations stay the same as Basic:

## Slide 14: Effort Adjustment Factors

## Slide 15: Example: Intermediate COCOMO
We need to develop an e-commerce platform with a project size of 70 KLOC. The project needs High Reliability, Complex Data Processing, Highly Skilled Team and Extensive use of Modern Tools.
Calculation:
  EAF =
  Base Effort =
  Adjusted Effort =
  Development Time =
  People Required =

## Slide 16: Detailed COCOMO
Advanced COCOMO Model: Builds on Intermediate COCOMO.
Phase-Sensitive Estimation: Estimates effort for each phase of the project (e.g., design, coding, testing).
Comprehensive Cost Drivers: Incorporates additional cost drivers for more precision.
Highest Accuracy: Provides the most accurate estimates for large and complex projects.

## Slide 17
Category | Cost Driver | Very Low | Low | Nominal | High | Very High | Extra High
Product | RELY | 0.75 | 0.88 | 1.00 | 1.15 | 1.40 | -
 | DATA | - | 0.94 | 1.00 | 1.08 | 1.16 | -
 | CPLX | 0.70 | 0.85 | 1.00 | 1.15 | 1.30 | 1.65
Hardware | TIME | - | - | 1.00 | 1.11 | 1.30 | 1.66
 | STOR | - | - | 1.00 | 1.06 | 1.21 | 1.56
 | VIRT | - | 0.87 | 1.00 | 1.15 | 1.30 | -
 | TURN | - | 0.87 | 1.00 | 1.07 | 1.15 | -
Personnel | ACAP | 1.46 | 1.19 | 1.00 | 0.86 | 0.71 | -
 | AEXP | 1.29 | 1.13 | 1.00 | 0.91 | 0.82 | -
 | PCAP | 1.42 | 1.17 | 1.00 | 0.86 | 0.70 | -
 | VEXP | 1.21 | - | 1.00 | 0.90 | - | -
 | LEXP | 1.14 | - | 1.00 | 0.95 | - | -
Project | MODP | 1.24 | 1.10 | 1.00 | 0.91 | 0.82 | -
 | TOOL | 1.24 | 1.10 | 1.00 | 0.91 | 0.83 | -
 | SCED | 1.23 | 1.08 | 1.00 | 1.04 | 1.10 | -
 | PVOL | - | 0.87 | 1.00 | 1.15 | 1.30 | -
 | PCON | - | 0.88 | 1.00 | 1.15 | 1.30 | -

## Slide 18: Example: Detailed COCOMO
We need to develop enterprise software with a size of 100 KLOC. The project phases are:
  Requirements: 30%
  Design: 30%
  Coding: 40%
  Effort Adjustment Factors are
  Platform Volatility (PVOL = 1.2)
  Personnel Continuity (PCON = 0.9)
  Database Size (DATA = 0.94)
  Analyst Capability (ACAP = 0.86)

## Slide 19: Example: Detailed COCOMO
Calculation:
  EAF =
  EAF =
  Base Effort =
  Adjusted Effort =
  Development Time =
  People Required =

## Slide 20: Example: Detailed COCOMO
Calculation:
  We Have Total Effort: 851.22PM, Dev Time: 22.44, Persons: 37.93
  We can now divide these costs for each phase as given:
  Requirements 30%
    Effort: 255.37 PM, Dev Time: 6.73 M, Persons: 37.93
  Designing 30%
    Effort: 255.37 PM, Dev Time: 6.73 M, Persons: 37.93
  Coding 40%
    Effort: 340.49 PM, Dev Time: 8.98 M, Persons: 37.93

## Slide 21: Advantages Of Using COCOMO
Cost Estimations
Resource Management
Risk Mitigation
Better Planning

## Slide 22: But There are Limitations to it ….
Assumes Static Requirements
Accuracy Depends on Historical Data
Ignores Modern Development Practices
Not Precise Enough

## Slide 23: COCOMO II
Enhancing Software Development Cost Estimation

## Slide 24: Need for COCOMO II
01

## Slide 25: Introduction
Enhanced version of the original COCOMO developed at the University of Southern California.
It addresses the limitations of its predecessor and offers improved methodologies for estimating the cost of software development.
The accurate estimation of cost, effort, and schedule is crucial for successful software project management.
02

## Slide 26: Stages for estimation:
Application composition
Early design
Post architecture
03

## Slide 27: Application composition
03-a
External features of the system that the users will experience are designed.
Prototyping will typically be employed to do this.
Object Point Counting

## Slide 28: Early design
Fundamental software structures are designed; such as the architecture, data models, and key algorithms, are designed
With larger, more demanding systems careful attention will be needed.
Function Points (FP): to quantify the size and complexity of a software applications functionality
03-b

## Slide 29: Post architecture
Here the software structures undergo final construction, modification, and tuning to create a system that will perform as required.
03-c

## Slide 30: Effort estimation formula
PM = A * Size * EM
PM is the estimated effort in person-months,
A is a constant value determined by the COCOMO II model,
Size is the size of the software project, typically measured in object points or EM is the effort multiplier, which adjusts the estimate to account for various productivity factors.

## Slide 31: Effort Multipliers

## Slide 32
Effort multipliers are applied to the basic effort estimation formula to account for these factors, allowing for a more accurate estimation of the overall development effort.

## Slide 33
We have a software project in the application composition stage estimated at 500 object points. With a constant value (A) of 2.5 and an effort multiplier (EM) set at 1.2, we can calculate the effort required
Calculation:
PM = A * Size * EM
Substitute the values
PM = 2.5 * 500 * 1.2 PM
= 1500 person-months

## Slide 34: — Note
Implementing COCOMO 2 requires expertise in estimation techniques, making it challenging for organizations to adopt without proper training.

## Slide 35: Best Practices for Using COCOMO 03

## Slide 36: Best Practices
Recognize the Assumptions Underpinning the Model:
Understand the model’s assumptions about team experience, size, and complexity.
Customize the Model:
Adapt COCOMO to fit your project’s unique needs and industry standards.
Utilize Historical Data:
Verify inputs and improve parameters with data from previous projects.
Verify and Validate:
Compare estimates with actual project results and adjust as needed.

## Slide 37: Comparison of COCOMO I and COCOMO II

## Slide 38: Comparison
Aspect | COCOMO I | COCOMO II
Model Types | Basic, Intermediate, Detailed | Application Composition, Early Design, Post-Architecture
Basic | Founded on linear reuse formula | Based on the non-linear reuse formula
Project Categories | Organic, Semi-Detached, Embedded | No rigid categories; uses scaling factors and cost drivers
Parameters | 17 cost drivers | 22 effort multipliers, 5 scale factors
Flexibility | Less flexible, suitable for simpler projects | More flexible, adaptable to different development stages

## Slide 39: Comparison
Aspect | COCOMO I | COCOMO II
Accuracy | Provides rough estimates | Provides more accurate estimates
Complexity | Simpler, easier to use | More complex, detailed
Model Framework | Development begins with the requirements assigned to the software | It follows a spiral type of Development.
Suitable Applications | Small to medium-sized projects | Medium to large, complex projects

## Slide 40: Thank you
"In software development, accurate estimation is the cornerstone of successful projects."

## Slide 41: —SPM
Hanzla Nouman
Laiba Binta Tahir
Arfah Ali